## AP
2020-2021
Strategic goal 1. Increase the role of self-governments in managing a substantial share of public affairs
Objective | Activity | Performance Indicator | Agency in Charge | Partner Organization | Time frame | Estimated budget (GEL) | Funding Source
Objective 1.1 Ensure full implementation of powers granted by the law to self-governments | 1.1.1. Identify factors hampering full implementation of competences by self-government units. | Research conducted to identify challenges for full execution of powers (at least 2 powers including one concerning local economic development) prescribed to the local self-governments by the law. | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 | 29000 | Development partners
| 1.1.2. Support to the implementation of competences granted by law upon self-government units | Respective legislatve changes are drafted and initiated with respect to at least 2 competences (one of them related to local economic development) | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 - 2021 | 10000 | Development partners
Objective 1.2 Inrease competences of local self-governments based on the principle of subsidiarity | 1.2.1. Define powers to be transferred to municipalities in accordance with the principle of subsidiarity | Research conducted to identify areas (at least one) in which competences may be transferred to local authorities | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia | 2020 | 8550 | Development partner
| 1.2.2. Ensure legal framework for the implementation of additional competences by self-government bodies | Specific competences (at leat two) as per identified areas and forms and timeframe of their transfer to municipalities identified. | Minisry of Regional Development and Infrastructure of Georgia | Municipalities Respective state agency | 2020 - 2021 | 45000 | Development partners
|  | Respective legal framework and/or by laws are developed | Minisry of Regional Development and Infrastructure of Georgia | Respective state agency | 2020 - 2021 | 5000 | Development partners
| 1.2.3. Ensure technical and financial support for municipalities for the execution of their additional competences | The rule for calculating matiarl and financial resources necessary for local self-governments to execute each of delegated competences drafted | Minisry of Regional Development and Infrastructure of Georgia | Respective state agency | 2020 - 2021 | 10000 | Development partners
Strategic goal 2 – Ensure adequate material and financial resources for local self-governments
Objective | Activity | Performance Indicator | Agency in Charge | Partner Organization | Time frame | Estimated budget (GEL) | Funding Source
Objective 2.1 Support consistent increase of local government's own revenues | 2.1.1. Revision local fees | Various practices pertaining to local fees are examined and recommendations developed | Minisry of Regional Development and Infrastructure of Georgia | Ministry of Finance of Georgia | 2020 | 52050 | Development partners
| 2.1.2. Transfer part of license to use fees to local self-governments | Types of licenses to use to be transferred to local self-governments identified and recommendations developed | Minisry of Regional Development and Infrastructure of Georgia | Various agencies | 2021 | 10000 | Development partner
| 2.1.3. Revise the rule for calculating property tax, taxpayers and taxable objects | Various practices of calculating the amount of property tax examined and recommendations developed | Ministry of Finance of Georgia | Minisry of Regional Development and Infrastructure of Georgia | 2020 | 34200 | Development partner
| 2.1.4. Transfer of property | Types of property to be transferred to municipalities, as well as rules, terms and procedures of the transfer are identified, and respective legislative changes drafted and passed. | Ministry of Economy and Sustainable Development of Georgia | Minisry of Regional Development and Infrastructure of Georgia; Municipalities | 2020 - 2021 | 30000 | Development partner
Objective: 2.2.Improve mechanisms for the allocation of state resources | 2.2.1. Improve the principle for revenue distribution | To conduct analysis of the results from the distribution of value added tax (related to the principles and methodology of its calculation) and prepare relevant recommendations | Ministry of Finance of Georgia | Minisry of Regional Development and Infrastructure of Georgia | 2020 - 2021 | 15000 | Development partner
| 2.2.2. Improve mechanisms for providing funds for the implementation of delegated competences by local self-governments | Respective legislative changes drafted | Ministry of Finance of Georgia | Minisry of Regional Development and Infrastructure of Georgia | 2020 | N/A | State budget
Strategic goal 3 – Develop reliable, accountable, transparent and results oriented self-governments
Objective | Activity | Performance Indicator | Agency in Charge | Partner Organization | Time frame | Estimated budget (GEL) | Funding Source
Objective: 3.1 Introduce effective and innovative management and quality service delivery systems at a local level | 3.1.1. Further improve management systems and administrative structure of local self-governments | A unified electronic system for the management of information flows introduced in at least 42 municipalities | Minisry of Regional Development and Infrastructure of Georgia | Municipal Service Development Agency | 2021 | 3400000 | State budget Development partners
|  | The rule for setting up legal entities under private law by municipalities revised | Minisry of Regional Development and Infrastructure of Georgia | Civil Service Bureau | 2020 | 10000 | Development partners
| 3.1.2. Improve the system of public finance management at a local level | Findings of Public Expenditure and Financial Accountability Assessment at sub-national level (PEFA) are analyzed in at least 35 municipalities | Ministry of Finance of Georgia | Municipalities | 2020 | 124000 | Development partner
|  | In order to address gaps identified as a result of Public Expenditure and Financial Accountability Assessment at a sub-national level (PEFA), mechanisms are introduced in up to 20 municipalities | Ministry of Finance of Georgia | Municipalities; Minisry of Regional Development and Infrastructure of Georgia | 2020 - 2021 | N/A | State budget
|  | In order to encourage the practice of results oriented planning (program budgeting), trainings and working meetings are held for at least 35 municipalities | Ministry of Finance of Georgia | Municipalities | 2020 | 124000 | Development partners
|  | At least 7 municipalities have been assisted/supported during the budget process and their program budget documentation prepared in accordance with the updated methodology of program budgeting (Priority Document, Action Plans, Program Budget Annex) | Ministry of Finance of Georgia | Municipalities | 2020 | 60000 | Development partner
|  | Budget guidelines prepared in at least 15 municipalities | Ministry of Finance of Georgia | Municipalities | 2020 | 45000 | Development partner
| 3.1.3. Build capacity of staff working for local self-governments | Training needs of municipal public servants are assessed in at least 5 areas | Civil Service Bureau | Minisry of Regional Development and Infrastructure of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 | N/A | State budget
|  | At least 30 learning activities with the purpose of enhancing qualification of municipal public servants carried out (at least 3000 public servants retrained) | Minisry of Regional Development and Infrastructure of Georgia | Municipalities Association of Finance Officers of Georgian Local Self-Governing Units | 2020 - 2021 | 925000 | Development partners
| 3.1.4. Adopt unified (minimal) standards for the delivery of municipal services and support to effective delivery of municipal services | Study on citizens' satisfaction with public services in Georgia carried out and findings published | Minisry of Regional Development and Infrastructure of Georgia |  | 2020 - 2021 | 200000 | Development partners
|  | Assessment of municipal service delivery in at least one area carried out in 20 municipalities | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 | 70000 | Development partners
|  | Criteria for the assessment of effectiveness of services developed | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 | 50000 | Development partners
| 3.1.5. Develop Intermunicipal Cooperation | Needs assessment for the development of Intermunicipal Cooperation carried out | Minisry of Regional Development and Infrastructure of Georgia | Municipalities "National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 | 35000 | Development partners
|  | A textbook to support Intermunicipal Cooperation prepared | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 | 5700 | Development partner
|  | Respective legislative changes prepared in support of Intermunicipal Cooperation | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2021 | 5000 | Development partners
|  | At least two new cases of Intermunicipal Cooperation | Municipalities | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2021 | 210000 | Development partner
| 3.1.6. Develop a mechanism for the collection of reliable statistical data pertaining to each of municipalities for informed decision-making | Statistical data to be collected at a local level identified | National Statistics Office of Georgia Municipalities | Minisry of Regional Development and Infrastructure of Georgia | 2020 | 60350 | Development partners
|  | Respective procedures and methodology developed | National Statistics Office of Georgia Municipalities | Minisry of Regional Development and Infrastructure of Georgia | 2021 | 50000 | Development partners
| 3.1.7. Support Public Private Partnership at a local level | Recommendations developed for improved Public Private Partnership | Minisry of Regional Development and Infrastructure of Georgia | Public-Private Partnership Center | 2020 | 60000 | Development partners
|  | Investment profiles created for at least 8 municipalities | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 | 80000 | Development partner
Objective 3.2. Implement high standards for transparency and accountability | 3.2.1. Support Open Governance Program in all municipalities of Georgia | Local authorities carry out activites under Open Governance Program and prepare reports with the engagement of civl sector and other stakeholders (in at least 16 municipalities) | Municipalities | Minisry of Regional Development and Infrastructure of Georgia | 2020 - 2021 | 141150 | Development partners
Objective 3.3. Facilitate effective participation in decision-making and implementation municipal level | 3.3.1. Improvement of the legislative framework and mechanisms in order to ensure stakeholders high quality of engagement in the decision-making and implementation process | Challenges for application of civic engagement forms are researched/identified | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 - 2021 | 10000 | Development partner
|  | Changes are prepared to improve public participation mechanisms | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia Association of Finance Officers of Georgian Local Self-Governing Units | 2020 - 2021 | 5000 | Development partners
| 3.3.2. Ensure public participation in the implementation of decentralization strategy | Communication plan developed and working, feedback is collected and analyzed routinely | Minisry of Regional Development and Infrastructure of Georgia | Municipalities National Association of Local Authorities of Georgia | 2020 - 2021 | 415000 | Development partners
| 3.3.3. Support gender equality at a local level | Gender needs assessment conducted at a local level (in at least 23 municipalities) and findings of the assessments made available | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 | 30000 | Development partner
|  | A conference on gender issues held | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 - 2021 | 50000 | Development partner
| 3.3.4 Increase youth participation in decision-making process at a local level | Capacities are built in the areas including but not limited to civic activism and advocacy (in at least 5 municipalities) | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 | 324000 | Development partners
Objective 3.4. Set up a system for local planning and coordination | 3.4.1. Legal arrangements for development planning | Study into the national and international practices conducted and recommendations prepared | Minisry of Regional Development and Infrastructure of Georgia | Administration of the Government of Georgia | 2020 | 29000 | Development partners
| 3.4.2. Create a methodological framework and standards for development planning | A textbook on methodology developed | Minisry of Regional Development and Infrastructure of Georgia | Administration of the Government of Georgia | 2020 | 29000 | Development partners
|  | Development planning documents developed by at least 39 municipalities | Minisry of Regional Development and Infrastructure of Georgia | Municipalities | 2020 - 2021 | 220000 | Development partners
|  | Localization plan and a guideline for Sustainable Development Goals (SDGs) developed | Administration of the Government of Georgia | Minisry of Regional Development and Infrastructure of Georgia | 2020 - 2021 | 10000 | Development partner
| 3.4.3. Introduce an effective system for monitoring, evaluation, and self-assessment of local self-governments | In order to support the implementation of good governance principles, the evaluation and self-assessment system has been developed | Minisry of Regional Development and Infrastructure of Georgia | National Association of Local Authorities of Georgia | 2020 | 115000 | Development partner
|  | In order to support the implementation of good governance principles, the evaluation and self-assessment system has been introduced to at least 5 pilot municipalities | Municipalities | Minisry of Regional Development and Infrastructure of Georgia National Association of Local Authorities of Georgia | 2021 | 105000 | Development partner
|  | Textbook for internal audit is developed for municipalities | Central Harmonization Unit | Minisry of Regional Development and Infrastructure of Georgia | 2020 | 32000 | Development partner
8 | 26 | 46 |  |  |  | 7278000
* Following development partners provide support to the implementation of the action plan: UNDP, SCO, ADA, DANIDA, USAID GGI, GIZ, EU